Consultation draft of the National Action Plan for Open Government 2018 - 2020
# Introduction
## Open Government in the UK
The UK is committed to Open Government and is a world leader in providing access to information, civic participation and public accountability. As a founding member of the Open Government Partnership, we know that opening up government is a powerful way of building trust and bringing people together, both nationally and locally. It helps build strong communities, drives economic growth, and improves government efficiency and service delivery.

Committing to the innovative pursuit of open government reform in the UK is also a foundation to promote and support the strengthening of democracy and transparency internationally.
## What is a National Action Plan for Open Government?
Every two years, each member nation of the Open Government Partnership creates a National Action Plan (NAP) setting out specific commitments to transparency, civic participation and public accountability.

National Action Plans set out a shared set of ambitions held by government and UK civil society in the pursuit of open government reform in the UK. They list specific commitments, milestones and timelines by which we can monitor progress and better enable civil society and citizens to hold Government to account.

The UK has now delivered three National Action Plans. Through these we have seen successes such as:

- The UK being the first G7 country to commit to the Open Contracting Data Standard (OCDS) for contracts administered by a central purchasing authority, the Crown Commercial Service. This means that the process of awarding public sector contracts - from bidding right through to building - was made public for the first time in 2016
- Leading the world in creating an open register of beneficial ownership so everyone can see who owns what in the UK..
- The introduction of reusable unique identifiers to the UK’s published government grants data and central procurement data. This represents a step change in how people can monitor how government is spending taxpayers’ money
## Implementation
In practical terms, this work is led by a joint steering committee for the Implementation of the NAP. This committee is made up of government and civil society leaders, who:

- meet quarterly to ensure commitments are met following the launch of the NAP maximise participation and cooperation between government and civil society
- proactively support innovative initiatives that increase openness, going beyond the National Action Plan
## What the Plan is not
This plan does not, however, seek to list every reform currently being delivered by UK Government in pursuit of openness, transparency and anti-corruption.
## The co-creation process
True to the spirit of Open Government, the UK’s National Action Plans are developed in close collaboration with citizens and civil society.

This year the Open Government Network has led the early consultation process, through an ideas crowdsourcing initiative and events around the country. The development has also been overseen by a Multi-stakeholder Forum made up of government officials and elected members of the Open Government Network representing civil society organisations.

The Open Government Network’s idea gathering and development culminated in the publication of its Open Government Manifesto 2018 - setting out priority areas which we’ve sought to address within this plan. These are:

- follow the money in government (transparency of government budgets, grants, contracts and spending)
- law, participation and policy (enabling open decision making processes where citizens can participate effectively)
- strengthening accountability and anti-corruption mechanisms
- building open data infrastructure for action

This consultation document represents the culmination of the co-creation process so far and sets out a set of early draft commitments for further comment. In the spirit of Open Government, we aim to share thinking as it develops and this does not represent a final Government policy approach.
## How to use this document
This consultation is an important stage in the development process through which to strengthen the plan. Constructive external challenge is vital to this. We are grateful for your time in reviewing this document and sharing your feedback.

1. This Google Doc has been created for the purpose of consulting on the UK’s draft National Action Plan for Open Government (2018 - 2020).
2. You’re welcome to make comments and suggestions directly in the document, using the comments function - highlight part of the document, then select the + box to add a comment. Please note that this is a public Google Doc, and any comments you make will be visible publicly. It is, therefore, advisable that you ensure your comments are in line with your organisation’s policies and public position.
3. If you’re commenting on behalf of an organisation please make it clear which organisation you represent within your feedback.
4. We welcome involvement from a broad range of organisations. If your organisation is supportive of or would like to be involved in further development or delivery of a commitment, please add your organisation’s name to the list of ‘other actors involved’.
5. Any abusive or offensive comments will be removed.
6. If you would prefer to comment anonymously, please email: opengov@culture.gov.uk

The consultation will be open from 5th September until 3rd October 2018, after which it will no longer be possible to comment on the document.
## Jump to …

# Commitment 1 - Grants data
Grants data
Lead implementing agency/actor		Cabinet Office, Department for Digital, Culture, Media and Sport (DCMS)
Commitment description
What is the public problem that the commitment will address?		The government spends more than £115bn a year on grants. Traditionally individual departments and teams have managed grants information internally. There was no central mechanism to collate data on grants and no reliable way of scrutinising government grants activity. / To address this, the Grants Function in the Cabinet Office developed the Government Grants Information System (GGIS), using agile methodology in line with Government Digital Service guidance and in accordance with user needs, to improve internal transparency by recording data in a standardised and scalable way. It collects information about grant funding across the whole of government, including grant making arms-length bodies. / This enabled Government to commit in the 2016 UK Government National Action Plan to publish grants data to the 360Giving standard, an open data standard for philanthropic giving. This commitment was delivered in October 2017 by the Cabinet Office Grants team publishing £100bn of grant spend data at scheme level, with two departments (MoJ and DfT) publishing at an award level to the 360Giving Standard. / Much progress has been made, but we must continue to publish even more granular grants data, both scheme and award level data, in line with the 360Giving Standard. / Government also wants to see a greater number of grant funders in the UK commit to greater transparency in publication of grants funding data, to support decision-making and learning across civil society. Improving this data landscape can support the development of a plural supply of public services. Publishing grants data to an open, standardised format means the information can be shared and compared. It will improve the impact and understanding of funding in the UK, and local accountability for public spending.
What is the commitment?		Working with users across government, the Cabinet Office Grants Efficiency Function will increase the transparency of government grant funding for the 2017/18 and 2018/19 financial years. / The Cabinet Office Grants Efficiency Function will continue to assist departments in ensuring that grant making across government is efficient and that funding is being used effectively. / DCMS will host a Ministerial event bringing together key sector partners to discuss how to collectively improve data infrastructure and open data publication to support the third sector.
How will the commitment contribute to solve the public problem?		The Government Grants Information System (GGIS) enables information on grant schemes (programmes) and the associated awards to be captured and shared with other government departments in a simple, standardised and scalable way. The insight obtained from the GGIS enables grant managers to improve the effectiveness of their grant making and ensure greater scrutiny by identifying areas of potential inefficiency or fraud throughout the grant making process. / The GGIS will reinforce our drive for efficiency, effectiveness and transparency in how we do our business in government and gives us greater assurance identifying and preventing fraud. / Publishing granular data in the 360Giving Standard makes the data more meaningful and useful both for government and for external users, as it is possible to see and compare grants made by charitable trusts and foundations alongside government grants. This makes it easier to identify gaps and overlaps as well as areas of need and to see changes in funding over time.
Why is this commitment relevant to OGP values?		This commitment supports transparency - disclosing more information, improving quality of the information disclosed, improving accessibility of information to the public or enabling the right to information.
Milestone Activity with a verifiable deliverable		Start Date:	End Date:
Publish more granular and even better quality data, to 360Giving Standards in the Autumn of 2018.		September 2018	Autumn 2018
DCMS Ministerial event with key sector partners - to discuss how to collectively improve data infrastructure, open data publication to support the third sector and ensure that the data is effectively used.		September 2018	January 2019
The 18/19 financial year granular data, in line with the 360Giving Standard will be published in the Autumn of 2019.		September 2018	Autumn 2019
DCMS and its Arm's-length bodies will ensure all relevant grants data is uploaded on the Government Grants Information System at awards level including third party data from onward grantees, in line with 360Giving.		September 2018	Autumn 2018
Other Actors Involved	State actors involved	Cabinet Office, DCMS
	CSOs, private sector, multilaterals, working groups	360Giving

# Commitment 2 - Public participation in digital and data policy development
Public participation in digital and data policy development (through the Digital Charter)
Lead implementing agency/actor		DCMS
Commitment description
What is the public problem that the commitment will address?		Technological developments and data-enabled innovations are causing fundamental changes to the way we live and work around the world. / It’s vital to the UK economy that we not just adapt to these changes, but be frontrunners in adopting new technologies and setting new norms and rules for the next generation of emerging technologies, like the Internet of Things, artificial intelligence and Blockchain. We must stimulate innovation and growth, ensuring that innovations are harnessed to deliver maximum public good. / Technology can act as an enabler for social good and community cohesion. Communities are using social networks such as Facebook and WhatsApp to connect those in need to local support, while crowdfunding is creating a new fundraising platform for charities and social enterprises. / But there are also risks and challenges. The internet will also be used to spread terrorist material or as a tool for abuse and bullying. It can undermine civil discourse, objective news and intellectual property. Such trends are deeply concerning for the pursuit of Open Government reform and citizen participation, because public trust is at the heart of these goals. / The Government’s Digital Charter is our response to these challenges: a rolling programme of work to agree norms and rules for the online world and put them into practice. / Because technological change is taking place so fast, it’s vital that we create flexible open structures for dialogue with citizens, civil society, academic experts and business. / We must continue to develop the Charter collaboratively, and to ensure we’re applying the principles of collaboration and openness to challenges in this space such as unlocking the power of data within Government and in the UK economy, while building public confidence in its use.
What is the commitment?		We’ll work with civil society, including through the Open Government Network, to ensure that as the Digital Charter is developed, it is made as easy as possible for citizens and others to share their views. / We’ll leverage the Open Government Partnership’s peer network to build international dialogue in support of the Charter’s aims. / We’ll ensure that principles of openness and citizen participation are built into the operation of the new Centre for Data Ethics and Innovation, which will advise government and regulators on the implications of new data-driven technologies, including AI. / We’ll ensure that Government’s National Data Strategy is developed in a participative way and informed by robust ongoing dialogue with a diverse range of voices from business, the third sector, civil society and data users. In relation to Government’s own use of data, we’ll maximise the use and value of public data, building and supporting a strong data economy, while also ensuring we maintain and build public trust in the use of data. / The Government committed to the principles of the International Open Data Charter in 2013, and we have since published over 44,000 datasets on Find Open Data (formerly data.gov.uk). Quantity is not enough, however and quality, reliability and accessibility are also required. Too much data is still published in PDF and other formats that are not machine-readable. DCMS will undertake a review of Government open data, including the challenges and barriers to publishing in a machine-readable and structured format and the datasets which could offer most value if improved. It will also develop a strategic approach to addressing these issues to improve open data within government.
How will the commitment contribute to solve the public problem?		Because of the speed at which technology is developed, and the cross-border nature of data-driven technologies, we need to develop new mechanisms for building open dialogue and principles of collaboration and inclusivity into Government’s policy development and delivery approach. / This set of commitments will inform the Government’s Digital Charter by strengthening the basis and mechanisms for participation and collaboration.
Why is this commitment relevant to OGP values?		This commitment supports civic participation - improving opportunities and capabilities for a broad and representative public to inform or influence decisions; creating or improving the enabling environment for civil society.
Milestone Activity with a verifiable deliverable		Start Date:	End Date:
Ensure that principles of openness and civic participation are built into the operation of the new Centre for Data Ethics and Innovation		November 2018	Ongoing
Further develop and maintain open dialogue with data users and civil society to support the development of the Government’s National Data Strategy.		September 2018	Ongoing
Review of HMG’s Open Data publication, which will identify the key challenges and opportunities of publishing more in machine-readable, standard, openly licenced formats, and set out measures to address this.		September 2018	July 2019
Other Actors Involved	State actors involved	DCMS, GDS

	CSOs, private sector, multilaterals, working groups	Open Data Institute / Open Rights Group

# Commitment 3 - Embedding Open Policy Making across HMG
Embedding open policy making across HMG
Lead implementing agency/actor		Cabinet Office
Commitment description
What is the public problem that the commitment will address?		Open Policy Making (OPM) is a way government can create and deliver policy that meets the demands of a fast-paced and increasingly digital world. It means that policy is more informed and better designed for both the government and the people who use or are impacted by services. Open policy makers design around the human experience, enable co-design supported by evidence and test policies as they develop them. / A core element of OPM is ensuring that evidence is used in a transparent and open manner. This enables policy makers to have a common understanding of people's needs and for civil society to understand the evidence base that has informed decision making. It also provides opportunity to see if there are gaps in the knowledge base and where further research might be commissioned. / But understanding the theory and delivering OPM in practice are not one and the same. OPM is not yet fully embedded across HMG, and we have not yet fully realised its potential. / It is vital that Open Policy Making is not an ‘add on’ to policy makers day to day work. It should be embedded across Government organisations - at all levels and at all points in the policy making process. Policy makers need to be supported to develop and trial a range of different approaches, understanding when different approaches are most appropriate. / Further, citizen and end-user engagement is a continuously developing field, with different tools and techniques developed on an ongoing basis. The Government also has great expertise to draw on. Meeting people’s needs has always been at the heart of GOV.UK’s mission. HMG can learn a lot about citizens’ needs and behaviours from their interactions with government online. This can help us to be more responsive to users, develop better services, and inform more effective policymaking. / Our commitment is to add content to the Open Policy Making Toolkit on GOV.UK and to consider the best way to communicate those tools. We suggest work in this commitment starts at a national level and, once evaluation is conducted, learnings are shared with devolved regions and local government, many of which will already be practicing OPM.
What is the commitment?		To continue to develop resources to support policy makers to use open policy making methods. This means developing the Open Policy making toolkit and careful consideration of how to increase awareness and application of the tools amongst policy makers. As such, development should be based on a concrete understanding of the lived experience of making policy - considering the right points to embed best, and next, practice. Following user research with policy makers, Policy Lab will revise the toolkit. / Policy Lab will deliver at least four ‘demonstrator’ projects which put citizens at the centre of policy making and reach groups whose voices may otherwise not be heard. These are commissioned by departments across government. As part of the OGP, we commit to sharing the learning and best practice from these projects in three ways: / Integrating best practice into the Open Policy Making toolkit. / At least one post on openpolicy.blog.gov.uk for each project. / At the end of every project, hold an open reflective session for civil society groups to help us refine project learnings and disseminate them further. / As other commitments, the open and reflective session will feed into wider NAP governance. The Implementation group for the NAP will meet quarterly. Membership, ToR and notes of each meeting will be published on the Open Government Network’s website. / Policy Lab often work with departments to increase the transparency and accessibility of evidence (e.g. working with the Government Office for Science on the Future of Ageing). Where evidence is publicly accessible and synthesised into ‘evidence safaris’ or other visually compelling resources, Policy Lab commits to make those resources publicly available for use by citizens. / GOV.UK will work with civil society and Policy Lab to improve sharing and use of data from GOV.UK as openly as possible both across government and with citizens. This could include data about page traffic, user journeys, user feedback or search terms. GOV.UK and Policy Lab will help government to use this data by providing guidance on how it can be used and signposting policymakers and citizens to training and resources to help them analyse and interpret the data.
How will the commitment contribute to solve the public problem?		Open policy making is one means of civic participation. Citizen engagement, as part of that process, is a continuously developing field, with new evidence of benefits and limitations of different techniques in different settings emerging on an ongoing basis. There is no single correct model that should be adopted in any given scenario, but instead a range of possible approaches, the design of which needs to be adapted to the specific context of implementation as well as the user groups you are designing for. / It is, therefore, important that governments and civil society continue to explore the efficacy of different approaches to inclusive citizen engagement in different scenarios, but do so in an agile way that enables continued development of approaches, and encourages the sharing of best practice across both Whitehall and local government.
Why is this commitment relevant to OGP values?		This commitment supports civic participation - Improving opportunities and capabilities for the public to inform or influence decisions; Creating or improving the enabling environment for civil society
Milestone Activity with a verifiable deliverable		Start Date:	End Date:
OPM toolkit first refresh		September 2018	By end of 2018/19 FY (31 March 2019)
Deliver and demonstrate learnings from 4 projects, feeding into NAP governance		September 2018	End of 2018/19 FY (31 March 2019)
Increase accessibility of evidence where projects come up		September 2018	End of 2018/19 FY (31 March 2019
Other Actors Involved	State actors involved	Policy Lab, Cabinet Office / What works team, Cabinet Office / GDS

	CSOs, private sector, multilaterals, working groups	Children’s Rights Alliance for England, Sense about Science

# Commitment 4 - Transparency Data
Transparency Data
Lead implementing agency/actor		Cabinet Office, Ministry of Housing, Communities and Local / Government (MHCLG)
Commitment description
What is the public problem that the commitment will address?		Since 2010 the UK has been at the forefront of opening up data. The public and press need data to hold public bodies to account and the UK government needs to do all it can to help ensure the highest standards of public life. Greater / transparency can also help to drive improved performance / and accountability. Public bodies also need to deliver value for money, cut waste and inefficiency and ensure every pound of taxpayers’ money is spent in the best possible way.
What is the commitment?		To improve the accessibility and quality of the range of transparency data published by central and local Government. To consider how the range of transparency data can be enhanced and made as useful as possible to the public, business, the voluntary sector, Parliament and Government itself (starting by publishing a list of current and recent Ministers since 2010). / MHCLG will also develop a package of policy proposals to help and encourage councils to publish all the information they can (i.e. not personal or sensitive data) as a matter of / course. This will help to drive further efficiency and / innovation within the sector.
How will the commitment contribute to solve the public problem?		Ensuring that data for existing and any new transparency data commitments is focussed onimproving quality, reliability and accessibility and that they are in an open, standard, structured and usable format so that third parties & Government can re-use and create value from the data. / It will also make it easier for the public to see how effective national and local government is – how they are performing and using resources. / A list of current and recent Ministers since 2010 aims to improve the ability of the public and civil society organisations to create value from other transparency data that Government already publishes, such as Ministerial gifts, hospitality, travel and meetings data. This is because it will be easier to identify who was in a Ministerial position at a certain point in time.
Why is this commitment relevant to OGP values?		This is a commitment to transparency - disclosing data, improving the quality of the data that is captured and disclosed and improving the accessibility of information to the public.
Additional information		In December 2017 the Prime Minister wrote to Cabinet colleagues about her priorities for progressing the Government’s transparency agenda. In support of that agenda, the Cabinet Office is establishing a central Transparency Data team to oversee the network of transparency data leads and publishers across government departments. The Transparency Data team will support departments as they improve the timeliness, quality and accessibility of Government transparency data publications. The team will have a wider policy remit to consider how the range of transparency information captured and published by Government can be expanded where appropriate and made as useful as possible to the public, business, the voluntary sector, Parliament and Government itself. / In pursuit of these objectives the Transparency Data team will look outwards for feedback and input from users, including civil society organisations, as well as with colleagues across Government. / MHCLG will be taking forward the work to develop a package of policy proposals to help and encourage councils to publish all the information they can
Milestone Activity with a verifiable deliverable		Start Date:	End Date:
Develop a package of policy proposals to help and encourage councils to publish all the information they can (i.e. not personal or sensitive data) as a matter of course.		September 2018	December 2018
Publish a list of current Ministers as open data		September 2018	December 2018
Support data leads and central Government departments as they improve the timeliness, quality and accessibility of Government transparency data publications		September 2018	June 2020
Streamline the preparation and publication of transparency data, using digital solutions and data standards where appropriate		September 2018	June 2020
Identify needs for government transparency that might be fulfilled by amended or alternative transparency data publication		September 2018	June 2020
Publish data on Ministerial position holders back to May 2010		January 2019	March 2019
Identify datasets that might be published as transparency data and promote experimentation focused on adding value		September 2018	June 2020
Encourage a collaborative and innovative culture that seeks to maximise the value of the transparency data that Government publishes through data analysis, exploration and visualisation.		September 2018	June 2020
Contact information
Other Actors Involved	State actors involved	CO, DCMS, MHCLG

	CSOs, private sector, / multilaterals, working groups	mySociety

# Commitment 5 - Open Contracting: Local Engagement and Data Use
Open Contracting: Local Engagement and Data Use
Lead implementing agency/actor		MHCLG
Commitment description
What is the public problem that the commitment will address?		Public contracting makes a big difference to citizens at the local level, including: / Local government contracts to procure goods and services, often from local businesses / Contracts to dispose of assets, such as land and buildings / Social Impact Bonds for delivery of local public services. / Whilst there is a good policy framework for procurement transparency, and most authorities comply with requirements to publish above-threshold procurement to Contracts Finder, and to maintain Contracts Registers under the Local Government Transparency Code, there are gaps in implementation, accessibility and use of local data: / Implementation: although government guidance calls for contract documents to be published, very few authorities proactively disclose the text of their contracts. This has been the source of major controversy in cases such as Sheffield’s road maintenance contract which led to destruction of healthy trees, and Gloucestershire’s Waste Disposal contract, which an Information Commissioner’s Office tribunal ruled should be public. / Accessibility: local authority procurement data is often provided through third-party platforms that do not use the OCDS (even though it is now recognised as a government standard), and that don’t provide easy access to bulk data for analysis. Better accessibility of data would support citizen oversight, and data analytics by government itself. / Use: local businesses, citizens and journalists often lack the skills to make the best possible use of contracting information and data. This is limiting the extent to which data is being used for innovation and scrutiny.
What is the commitment?		Creating a coalition of partners to promote implementation, accessibility and use of open contracting at the local level through investment in capacity building. / We will also be publishing proposals to help encourage local / authorities to publish all of the contracting data they can (but not / personal or sensitive data) to make it easier for residents to / see how organisations are performing, to improve decision / making within councils, and help to drive improvements in / service design and delivery (see commitment 4). This shall include the development of guidance on transparency and open contracting in Social Impact Bonds for the delivery of local public services
How will the commitment contribute to solve the public problem?		This commitment will ensure there are clear signals from national government to support and mobilise local government action on open contracting. / The coalition will support scoping studies in local areas (including multi-authority Mayoral regions), in order to identify the opportunities for local open contracting initiatives to contribute to greater citizen participation, efficiency in procurement, innovation, and support for small businesses, third sector and mutuals. / The coalition will seek to develop a fund to support capacity building with local journalists, building on recent moves to increase reporting on local issues through the BBC’s local journalist funding. This should lead to expanded skills for the use of open contracting data and information.
Why is this commitment relevant to OGP values?		This commitment supports transparency - disclosing more information, improving quality of the information disclosed, improving accessibility of information to the public or enabling the right to information.
Milestone Activity with a verifiable deliverable		Start Date:	End Date:
Establish coalition		September 2018	December 2018
Support 5 local scoping studies		September 2018	June 2019
Develop a support scheme for local authority open contracting innovation		September 2018	June 2019
Work with researchers to evaluate impacts		September 2019	March 2020
Other Actors Involved	State actors involved	DCMS

	CSOs, private sector, multilaterals, working groups	Open Contracting Partnership, Open Contracting Data Standard Helpdesk, eProcurement system vendors

# Commitment 6: Open Contracting Data
Open Contracting Data
Lead implementing agency/actor		Cabinet Office
Commitment description
What is the public problem that the commitment will address?		Although there is increasing compliance with the requirement to publish contract opportunities and awards through the Contracts Finder platform, there remain data gaps and limitations that make it difficult for government, the private sector and citizens to understand the full pattern of government procurement and spending, and to identify who government is doing business with. / It remains difficult to answer questions such as: / How many contracts does government hold with Firm X? And how close to completion are these? / How many government tenders are being won by suppliers outside the UK? / How do contract terms and values for waste management contracts vary across public authorities? / How many contracts include a transparency clause supporting citizen oversight of delivery? / Building on existing foundations, a focus on better data should be able to answer these questions. / Although policy and guidance call for publication of contracting documents, these are also often not published: sometimes due to fears about commercial confidentiality restrictions. Recent mythbusting work has shown commercial confidentiality should not restrict most contract document publication. / Regarding Social Impact Bonds, tender invitation documents are sometimes available on Contract Finder, but the contracts and costs to government(s) are unavailable. This lack of transparency may make it difficult for the public to understand what services are being delivered through Social Impact Bonds, at what cost, and whether they are being delivered effectively.This lack of transparency may also make it difficult for local authorities and others to learn from each other and/or improve efficiency.
What is the commitment?		Improve compliance, coverage and quality of publication to Contracts Finder so that all above threshold public contracts can be tracked from planning to final spending. Social Impact Bond contract data and documents, including evaluations, will be included in these efforts to improve compliance.
How will the commitment contribute to solve the public problem?		This commitment will drive continued developments of the Contracts Finder platform, and UK implementation of the OC D S as a tool for transparency, accountability, efficiency and operational analytics. / Improving the use and validation of organisation identifiers will help to provide a view of government business with specific organisations, and will help identify the geographic origin and beneficial ownership of those organisations. / Work on bringing subcontracting data into the Contracts Finder platform will provide a clearer view of the government supply chain, including the presence of SMEs, third-sector and mutual providers of services. / Improving compliance with policy requirements and guidance to publish contract documents and contract data will assist analysis of how contract terms affect the price and delivery of public services. The creation of additional OCDS metadata fields in Contracts Finder to indicate specific types of contract terms (e.g. use of a transparency clause) will allow the consequences of outsourcing on citizens access to information to be monitored. / Working with the community to build analytics tools of Contracts Finder data will help government, private firms and citizens to use available data to be more informed about public procurement. / Work on contracts registers and spend linkage will support a move towards a much more integrated public financial infrastructure, where citizens can fully ‘follow the money’. / Providing transparency and open contracting guidance to the parties in Social Impact Bonds may help improve learning, management efficiency, and assessment of this public contracting mechanism.
Why is this commitment relevant to OGP values?		The commitment supports government efficiency and effectiveness, and citizen oversight of key government processes and spending. / Capturing metadata on use of contract transparency terms will both support an understanding of how the right to information is affected by outsourcing, and will act as an incentive for these terms to be adopted.
Additional information		UK anti-corruption strategy 2017 to 2022 https://www.gov.uk/government/publications/uk-anti-corruption-strategy-2017-to-2022
Milestone Activity with a verifiable deliverable		Start Date:	End Date:
Compliance:
Agree joint methodology with civil society for measuring, planning, tender and award publication		December 2018	March 2019
Achieve 80% of above threshold tenders and awards on Contracts Finder		December 2018	October 2019
Achieve 90% of above threshold tenders and awards on Contracts Finder		October 2019	June 2020
Report regularly on publication of contract documents, and extent of redactions.		January 2019	Quarterly until June 2020
Coverage:
Suppliers on larger central government contracts will have to advertise subcontracting opportunities via the Contracts Finder website.		September 2018	Ongoing
Design and introduce fields for reporting on use of model contract transparency clauses		April 2019	December 2019
Design and pilot features to maintain a contracts register and implementation progress information through Contracts Finder, supporting coverage from planning -> implementation.		April 2019	March 2020
Identifiers:
Publish buyer and supplier organisation identifiers for 90% of domestic awards, and all awards over £1m		April 2019	March 2020
Publisher supplier identifiers for 90% of international awards		April 2019	March 2020
Consult widely on the impact and implications of linking contracts and spend to identify opportunities for identifier exchange between procurement and financial systems		April 2019	December 2019
International - led by DFID:
Four government agencies in DFID priority countries regularly publish data in line with the Open Contracting Data Standard (OCDS) by June 2020, with assistance from Open Contracting Partnership (OCP).		September 2018	June 2020
Contact information
Other Actors Involved	State actors involved	Department for Digital, Culture, Media & Sport (DCMS), DFID

	CSOs, private sector, multilaterals, working groups	Open Contracting Partnership and the UK Open Contracting Steering Group / eProcurement system vendors

# Commitment 7: Natural Resource Transparency
Natural Resource Transparency
Lead implementing agency/actor		DFID
Commitment description
What is the public problem that the commitment will address?		Corruption and fiscal mismanagement in the international natural resources (oil, gas and mining) sector have long been a major concern for governments, extractive companies, investors and civil society. The UK and other countries have achieved good progress in promoting natural resource transparency and accountability over the last 15 years, through both voluntary reporting under the Extractive Industries Transparency Initiative (EITI) and mandatory reporting rules now in force in the UK, across the EU, in Canada and in Norway, and awaiting implementation in the United States. But significant gaps remain in the scope and coverage of extractive companies’ disclosures of payments to governments and in the clarity and accessibility of the disclosed data.
What is the commitment?		We will work with others to enhance company disclosure regarding payments to governments for the sale of publicly owned oil, gas and minerals and help to establish/implement a common global reporting standard. / · We will continue to lead an international dialogue on increased transparency around sales of publicly owned oil, gas and minerals. / · We will undertake a scoping study to review what potential national action the UK could take to enhance company disclosure around the world regarding sales of publicly owned oil, gas and minerals. As part of this review, we will consider a form of cross-departmental guidelines on reporting these specific payments to governments. / We will maintain our commitment to the Extractive Industries Transparency Initiative (EITI) and to implementation of the UK-transposed EU Directives for mandatory reporting by companies. / · In light of the Business, Energy and Industrial Strategy (BEIS) Post Implementation Review of the UK mandatory reporting regulations and the European Commission consultation in respect of the Accounting Directive chapter 10 (due end 2018), we will be open to working with stakeholders and delivery partners in exploring the scope for enhancing the effectiveness of reporting requirements. / · We will provide clarity for UK-listed extractive companies, under the Disclosure Guidance and Transparency Rules; transparency disclosures are required to be in both open machine-readable data format and in human-readable format suitable for dissemination to as wide a public as possible.
How will the commitment contribute to solve the public problem?		(1) The largest payment stream missing from mandatory disclosure is payments to governments for the sale of publicly owned oil, gas and minerals (commodity trading), an area where corruption risk is acute. Governments’ and state owned enterprises’ sales of the state’s production share in the extractive industries are huge, typically US$ billions per year, and vulnerable to large-scale abuse. From 2011 to 2013, for example, the total value of sales by the national oil companies of Africa’s top ten oil producers was equal to 56% of their combined government revenues and more than ten times international aid to these countries. At company level, total payments to governments for oil and gas by Swiss trader Trafigura amounted to US$21.2 billion in 2016, significantly more than the US$15.1 billion disclosed by Royal Dutch Shell, Europe’s largest oil company, as total payments for its oil and gas extraction around the world in the same year. Swiss-headquartered company Glencore voluntarily revealed it paid USD$12.6 billion to purchase crude oil from governments in 2017, almost five times more than its tax and royalty disclosures under the Transparency Directive. A further Swiss trader, Gunvor, has committed to make similar disclosures. No UK oil major has made a similar commitment, and while Swiss traders have revealed total payments above, they only disaggregate payments to the country level in EITI implementing countries, where the minority of their payments are made (Natural Resource Governance Institute figures). / (2) Extractive company reporting under UK transparency rules currently suffers from several deficiencies that clarification of the disclosures’ content and format would ameliorate: (a) non-inclusion by at least seven companies of their share of joint venture payments; (b) over-aggregation of projects by at least twelve companies; (c) non-identification of recipient government entities by at least 28 companies; (d) lack of volume data for, and over-aggregation of, in-kind payments by at least four companies; (e) failure of a number of UK-listed extractive companies to report under revised requirements for financial year 2017 in both open machine-readable data and human-readable format. The commitments will build on progress to date by continuing efforts to explore for, identify and (where practical and permissible) implement incremental enhancement in extractives transparency.
Why is this commitment relevant to OGP values?		Transparency and Accountability
Milestone Activity with a verifiable deliverable		Start Date:	End Date:
We will continue to lead an international dialogue on increased transparency around sales of publicly owned oil, gas and minerals.		September 2018	July 2020
The UK will undertake a scoping study to review what potential national action we could take to enhance company disclosure around the world regarding sales of publicly owned oil, gas and minerals. As part of this review, we will consider a form of cross-departmental guidelines on reporting these specific payments to governments in this sector.		September 2018	December 2018
We will maintain our commitment to the Extractive Industries Transparency Initiative (EITI) and to implementation of the UK-transposed EU Directives for mandatory reporting by companies.		September 2018	July 2020
In light of the BEIS Post Implementation Review of the UK mandatory reporting regulations and the European Commission consultation in respect of the Accounting Directive chapter 10 (due end 2018), we will be open to working with stakeholders and delivery partners in exploring the scope for enhancing the effectiveness of reporting requirements.		September 2018	August 2020
We will clarify for UK-listed extractive companies, under the Disclosure Guidance and Transparency Rules, that transparency disclosures are required to be in both open machine-readable data format and in human-readable format suitable for dissemination to as wide a public as possible.		September 2018	December 2019
Contact information
Other Actors Involved	State actors involved	DFID, BEIS, HM Treasury(HMT), Financial Conduct Authority (FCA)

	CSOs, private sector, multilaterals, working groups	Natural Resource Governance Institute (NRGI), Publish What You Pay UK (PWYP), Global Witness, Transparency International-UK, Oxfam GB and Open Contracting Partnership

# Commitment 8 - Innovation in Democracy
Innovation in Democracy
Lead implementing agency/actor		DCMS
Commitment description
What is the public problem that the commitment will address?		Between elections, the majority of UK citizens will experience very little influence in Government decision making at a local and national level. / We must continue to pursue new ways to involve citizens in Government decision-making; stimulate dialogue and promote understanding of the impact of policy making on everyday life. Both through promoting the benefits of such engagement, to citizens and Government officials and decision makers, and by sharing best practice and building skills and capability within Government.
What is the commitment?		To deliver a programme to involve citizens in local decision making through trialling innovative models of participatory democracy.
How will the commitment contribute to solve the public problem?		People are most likely to engage where they see the everyday impact of the decisions that are made, and feel they can make a difference by being involved. / We will be supporting 8-10 local authorities (LAs) to pilot Citizens’ Juries to empower participants to deliberate and make recommendations on a decision that the LA has to make, leading to real impact on local policy development and delivery. The face-to-face participation will be complemented by digital platforms to increase engagement and transparency.
Why is this commitment relevant to OGP values?		Civic participation - Creating or improving opportunities or capabilities for the public to inform or influence decisions
Additional information		This work has been developed as part of the Civil Society Strategy.
Milestone Activity with a verifiable deliverable		Start Date:	End Date:
Appoint Democracy Support Contractor (following an open competition)		October 2018	November 2018
Appoint local authorities which will take part in programme (following an open competition)		December 2018	December 2018
Pilots delivered		January 2018	March 2020
Evaluation		January 2018	March 2020
Contact information
Other Actors Involved	State actors involved	Department for Digital, Culture, Media and Sport.

	CSOs, private sector, multilaterals, working groups	Tapvote.org

[1] Natural Resource Governance Institute (NRGI) figures